## Sheet1
Time | Task | Responsible Party | Location | Notes
6:00 | Survey space and make sure all necessary access points are open | Venue Operators
| Block off parking for vendors and set up crews | Security
6:15 | Set up a HQ space | Head of the Operations team | Stage | this space will be where the head of operations is stationed so if there are questions members can ask them |  | Operations team- Google employees oparating and managing the event (green) Welcome Team- Volunteers helping out with the event and welcoming people into /around the venue (yellow) Volunteers- working throughout the venue (blue) Set up crews- red all other workers in (black) all teams will be in shifts
| Lawn work and up keep | Venue Operators
6:30 | AV Teams arrive |  |  | Check in with operations
| Check on sound system and screens | AV Teams | Stage
| Set up teams arrive |  |  | check in with operations
| Set up of Vendor Lounge- furniture, lighting | Set Up Team | Rehersal Room
7:00 | Set Up of Livestream set | AV and Set Up Teams | Stage
| Check on progress | Operations Team
| Tape off areas for vendors | Set Up Team | Green space
| Tape off all wires and make sure vendors have access to everything they requested | AV and Set Up Teams | Green Space
| Welcome teams arrive |  |  | Check in with operations
| Breakfast Break | Set Up Team, AV Team, and Operations Team |  | will be in shifts throughout 7:00 o'clock hour according to what work is accomplished
7:30 | Accept deliveries- drinks, snacks, gifts, sanitization stations | Set Up Team |  | Check in with operations
| Volunteers Arrive |  |  | check in with operations
| Package gift bags for vendors | Volunteers | Rehersal Room | masks, t-shirts, google merch
| Stock vendor lounge | Volunteers | Rehersal Room | drinks, snacks
| Placing Sanitization Stations | Set Up Team | Green Space
| Set up Sign-in desks and welcome signs for vendors | Welcome Team | Outside Venue
| Continue Livestream Set-Up | AV Teams | Stage
8:00 | Vendors Start to Arrive |  |  | Check in with operations. Every 15 minutes there will be 20 vendors coming.
| Photo Booth Set Up | Volunteers | Green Space | ballons, streamers, letters, wood structure
| Help With Vendors when needed | Set Up Team | Green Space
| Continue Livestream Set-Up | AV Teams | Stage
| Parking and traffic direction | Security | Parking lot
8:30 | Trial run of Livestream | AV Team | Stage
| set up of lawn games | ChicagoCares Volunteers | Green space
| set up of bikeshare bikes around the park | DIVY | Around Millenium Park | if help is needed as operations team
| continue decoration set-up | Set Up Team and Volunteers | Green Space | banenrs, streamers, balloons, signs
| Check-in with venues around the nation | Operations Team | Stage/Livestream Space
9:15 | Take down welcome station for vendors, convert it into welcome station for guests | Welcome Team | Outside Venue
| Finish final touches for livestream set up | AV and Set Up Teams | Stage
| Quick break and/or shift changes for volunteers | Operations Team | Back Stage
9:30 | Prepare for guest set up | Welcome Team
| Round 1 of sanitization | Sanitization Team | Whole Venue | every hour and a half, teams will check on trash levels, sanitize any common touch points for vendors or guests and keep up with maintanence | *on-going event
| Traffic and Parking Set-Up | Security
Set-up Teams Dismissed
10:00 | OFFICIAL START TIME OF EVENT |  |  | *vendors control what happens at their individual stations throughout the event
| Welcome guests | Welcome Team and volunteers | throughout the park and at entrance | each member equiped with an IPAD
| Start the Livestream | AV Team
10:30 | Interviews of Vendors | Operations Team | Rehersal Room | every 30 minutes vendors who paid for livestream screen time will be interviewed during their time slot | *on-going event
| Live Stream of event and guests | AV Team | Green space
11:00 | Round 2 of Sanitization | Sanitization Team
| live Interviews of Vendors | Operations and AV team | Stage
| Recordings of vendors for livestream | AV Team | livestream | * videos vendors have sent in due to not coming to the event
11:30 | Shift change | for all | back stage
| Break for Snacks | for all | back stage | in shifts
12:00 | Round 3 of sanitization | Sanitization Team
| live Interviews of Vendors | AV and Operations Team | stage
| restock sanitization stations and water for guests | Volunteers
12:30 | Live Stream of event and guests | AV Team | Green space
| restock of snacks, water, and goodies for vendors | Volunteers | rehersal room
| prepare for vendors leaving and coming in | Welcome team |  | new tables and designated signs for easy pack up and move in of vendors during the event
13:00 | live Interviews of Vendors | AV and Operations Team | stage
| Tear down for some vendors |  |  | vendors signed up for timeslots of when they would be there and when they would tear down this is the middle tear down session
13:30 | Round 4 of sanitization | Sanitization Team
| Live Stream of event and guests | AV Team | Green space
| Set Up for mid-day vendors |  |  | check in with operations
14:00 | Recordings of vendors for livestream | AV Team | livestream
| restock sanitization stations and water for guests | Volunteers
14:30 | Shift change | for all | back stage
| break for snacks | for all | back stage | in shifts
15:00 | Round 5 of sanitization | Sanitization Team
| live Interviews of Vendors | AV and Operations Team | stage
| restock of snacks, water, and goodies for vendors | Volunteers | rehersal room
15:30 | Live Stream of event and guests | AV Team | Green space
| prepare for end of event | security
16:00 | Recordings of vendors for livestream | AV Team | livestream
Tear down crews arrive
16:30 | Round 6 of sanitization | Sanitization Team
| Wrap up of Livestream | AV Team
| Start set-ing up for shut down | Welcome Team
17:00 | Closure of the Event
Tear down